## Slide 1
Project Structure
Phone: +92 300 9440596
info@maxcoretechnologies.com
Machinery Rent System https://maxcoretechnologies.com/

## Slide 2: Milestone 1
Frond End Design of Admin Dashbaord
Admin Login (Admin can add new users)
All transactions will be made against two companies (Al asfar Technical Service LLC, International Capital Tower).
View, Add Machines
View, Add Companies
View, Add Employees
5 Business Days

## Slide 3: Milestone 2
Back End Functionalities for Admin Dashboard
Complete functionalities for Machines (Add, View, Update, Delete, reminder for expiry date, upload documents with expiry and reg date)
Complete functionalities for Employees (Add, View, Update, Delete, reminder for expiry date, upload documents with reg and expiry date)
Complete functionalities for Companies (Add, View, Update, Delete, upload documents)
Oil Records ( Add oil, use oil for equipments )
10 Business Days

## Slide 4: Milestone 3
Back End Functionalities Rent Wordflow
When any company will send mail for rent. Then admin will create quotation and will send to company (quotation can be update). At the end of discussion one entry will be created when machine will send to company and after receiving machine, rent will be calculated according to agreed amount per hour. After that invoice will be created.
7 Business Days

## Slide 5: Milestone 4
Reporting (Frontend & Backend)
Machine Report
Income Report with filters (for specific month, between starting and ending date, for specific machine, for specific company, for specific employee)
Quotation
LPO (Consumable & Hire)
Machinery Invoice
Service Vehicle List
Vehicle Renewal Detail
Vehicle Status
Backup Feature
15 Business Days

## Slide 6
Payment & Estimated Time:
Your project will include following steps:
1st Milestone: 15% Payment
2nd Milestone: 35% Payment
3rd Milestone: 20% Payment
4rd Milestone: 30% Payment

## Slide 7
Our Development process:
We take a structured approach to web design. Our development process was created to ensure every project is delivered on-time and on budget. We use Laravel framework of php language for admin dashboard.
Initial Planning:
Firstly, our team sit with your team and create detailed set of technical specification . These specifications serve as a roadmap for the rest of software development.
Development:
At this time, we will start the technical side of web.
Testing:
Once our developer have finished their work, our team will get to work testing your software performance and reliability. We will use different tools to benchmark your site for loading, responsiveness and speed, while also ensuring that it works reliably on the web browsers.